## Overview
COMFYUI CONTROL ¦ Road to 1.0
Manual test log · planned 18 October 2026 · Europe/Berlin
1 Record the exact setup you test
App version / commit | 0.11.2.dev6 / 6bd3728
Branch / install type | testing/nfs-output · fill in: venv / ZIP / RPM
Actual test date / tester
Fedora / Plasma version
ComfyUI version / Python
GPU / driver / ROCm or CUDA
iPhone / iOS / browser
NAS / export / NFS version
Local output / workflow names
2 Start with Tonight; filter Status to find unfinished tests
Work through Tonight in order. Before 1.0 contains packaging checks and the broader regression pass; some need a release-candidate RPM later.
Use the Status dropdown. Record what actually happened, plus the image filename, exact error, screenshot/log reference and issue ID. A successful automated test is not a manual Pass.
Pass means the expected result was observed. Fail = wrong behavior; Blocked = cannot perform the test yet; Not applicable = explain why. All tests start at Not run.
If a test fails, add a row on Issues. After a fix, record the new build/date and retest result; retain the original failure notes.
Run NAS outage tests on a test export when safe for its other users. Restore the NAS first if an NFS save waits. Existing fallback files require manual upload.
3 Progress — all manual results are initially untested
Plan | Tests | Pass | Fail | Blocked | Not run | N/A
Tonight | 14 | 0 | 0 | 0 | 14 | 0
Before 1.0 | 16 | 0 | 0 | 0 | 16 | 0
4 Release review
Required tests remaining | 23 |  |  | Open critical/high issues | 0
TESTING INCOMPLETE
1.0 review: every Required test passes; Conditional checks are tested when applicable or have a reason recorded. Review every failure and accepted limitation. No unresolved critical/high issue. The summary is a review aid, not automatic release approval.
Start Tonight → |  |  |  | Record an issue →

## Tonight
TONIGHT ¦ Manual test cases
Start here: real NAS mount/saves, local fallback, mobile gallery and phone recovery. Run T14 last.
Edit blue cells. For each test, select a status and record an actual result; link failures to Issues. Keep the original failure when adding a retest result.
Overview
ID | Priority | Status | Test | Steps and expected result | Actual result / notes | Evidence / issue ID | Retest: build, date, result | Tested on
T01 | Required | Not run | Baseline: existing installation | STEPS Fill in Overview. Launch the testing app, select your existing installation and saved workflow, then start ComfyUI. EXPECTED Existing settings, launch flags, workflow mappings and models remain intact. Desktop stays responsive and ComfyUI starts normally.
T02 | Conditional | Not run | NFS client installation offer | STEPS Click Set up mount. If NFS tools are absent, first cancel the install offer, then accept it, complete installation in the terminal and click Set up mount again. Do not uninstall working NFS tools just to test this. EXPECTED Missing tools produce an optional install offer with the correct package. Cancel retains local fallback. Installed tools skip the offer. Installation and authorization finish in the terminal without freezing the app. If already installed, mark Not applicable and say why.
T03 | Required | Not run | Real NAS mount and write permission | STEPS Stop ComfyUI. Enable Network output, enter the NAS and export, save, then Set up mount. Review and authorize setup. Wait for the connection result. EXPECTED Network output becomes ready after an actual user write check. No repeated administrator prompt on normal startup. Record the mount location and any permission error.
T04 | Required | Not run | Desktop generation saves to NAS | STEPS With network output ready, start ComfyUI and generate a small image from your usual desktop workflow. Use a new seed and identifiable prompt. Check the NAS itself and Open output folder. EXPECTED The completed image really exists on the NAS with the expected name/time and opens correctly. A thumbnail alone is not proof that the file was saved to the right location.
T05 | Required | Not run | Mobile gallery reads NAS images | STEPS Scan the QR on your iPhone. Open Gallery, locate T04, view it full-size, open Details and save/download it. Refresh the page and repeat opening it. EXPECTED The NAS image loads in the gallery and full-size viewer, downloads successfully and remains accessible after refresh. Details show available metadata without invented values.
T06 | Required | Not run | Mobile generates usual custom workflow | STEPS Use your existing GGUF / LoRA / upscaling preset. Change the prompt and supported settings, Generate twice with randomize enabled, and inspect the output files on the NAS. EXPECTED Model preparation is visible before sampling; progress and the completed image appear. Repeated randomized submissions generate new work. Custom nodes, model choices, LoRAs and upscaling work; the original saved workflow is unchanged.
T07 | Required | Not run | NAS unavailable at app startup | STEPS Stop ComfyUI and close the app. Make only the test export unavailable, then relaunch the app. Record the time to a usable window and the eventual error. Restore the NAS after T09. EXPECTED The desktop opens without waiting for the NAS. The background check ends with an understandable error and local-fallback/manual-upload warning. The app stays usable; it does not claim the mount is ready.
T08 | Required | Not run | Fallback saves to ComfyUI/output | STEPS While the NAS is still unavailable, start ComfyUI and generate an image. Check the selected installation’s local output folder and Open output folder. EXPECTED A real file is saved under this installation’s ComfyUI/output. It is not written to the unmounted /mnt directory. The warning names the local folder and says to upload these images manually.
T09 | Required | Not run | Mobile follows local fallback | STEPS Keep the fallback run active. On the phone, open Gallery and the T08 image, download it and refresh. Check both Create and Gallery for the warning. EXPECTED The mobile gallery reads the local fallback folder and the image opens/downloads. The mount error and manual-upload reminder are visible and survive refresh. Seeing only the old NAS thumbnails is not a pass.
T10 | Required | Not run | NAS recovery and deliberate switching | STEPS Restore the NAS and Retry network while ComfyUI still uses fallback. Generate once more. Then manually restart ComfyUI and generate again; check both locations. EXPECTED A successful retry does not redirect a running server. The first new file stays local; after restart the next is saved to NFS. Fallback files remain local for manual upload; no automatic copy or silent destination change occurs.
T11 | Required | Not run | Automatic connection after app restart | STEPS With the NAS available and Connect when app starts enabled, stop ComfyUI, quit completely, relaunch and wait for readiness before starting it again. Generate and open the image on the phone. EXPECTED Saved mount settings reconnect in the background without a new setup authorization. New output is on the NAS and mobile uses the same destination. Settings and the chosen workflow are preserved.
T12 | Required | Not run | iPhone lock, VPN loss and reconnection | STEPS Start a mobile generation. Lock the phone for several minutes, then unlock. Repeat with a short VPN/network interruption and a refresh; retain an unsent prompt edit during recovery. EXPECTED The existing job resumes live progress if still running, or shows its completed images if finished. No duplicate job is submitted. The unsent edit and selected workflow/settings survive. If VPN is unavailable tonight, record the missing part and leave this Blocked.
T13 | Required | Not run | Tray, restore and complete shutdown | STEPS During generation, close the desktop window and choose Keep in tray. Check phone progress, restore the window, then Stop ComfyUI. Finally Quit completely from the tray. EXPECTED Keeping in tray preserves generation and mobile access. Restore brings back the same window. Stop confirms owned processes stopped. Complete Quit stops owned children and the mobile listener; the app is not left hidden.
T14 | Required | Not run | NAS outage during active generation | STEPS Run last, using a test export when safe for other NAS users. Start an NFS-backed generation, temporarily make the export unreachable, click Retry network, and check desktop/mobile responsiveness. Restore the NAS before trying to finish shutdown or retrying. EXPECTED The app stays responsive and the failed retry reports the error. It explains that the active server still targets NFS and needs a manual restart for fallback. A hard-mounted save may wait or fail until the NAS returns; transparent redirection is NOT expected. Record the exact outcome and recovery.

## Before 1.0
BEFORE 1.0 ¦ Manual test cases
Follow-up checks: packaging plus existing functionality. R01 needs a release-candidate RPM; no build is requested by this workbook.
Edit blue cells. For each test, select a status and record an actual result; link failures to Issues. Keep the original failure when adding a retest result.
Overview
ID | Priority | Status | Test | Steps and expected result | Actual result / notes | Evidence / issue ID | Retest: build, date, result | Tested on
R01 | Required | Not run | Upgrade from stable RPM — release candidate | STEPS After an actual release-candidate RPM exists, record the installed stable version and back up the app’s settings. Upgrade using the intended package path, launch and check saved configuration. This check does not request a build now. EXPECTED Package installs/upgrades cleanly and the app starts. Existing installation paths, presets/mappings, mobile settings, history and recovery state are preserved. Record the RPM version and exact command used.
R02 | Required | Not run | Fresh app install and first-run setup | STEPS Use a clean test user/profile or disposable environment. Install the candidate package or test download. Choose an existing ComfyUI installation and test Start/Stop. EXPECTED No developer checkout, screenshots or test dependencies are needed. First-run setup works, the app/menu icon is present and normal user permissions are sufficient for running the app.
R03 | Conditional | Not run | Install ComfyUI into a new environment | STEPS Use a new disposable path, not your working ComfyUI directory. In first-run setup choose Install with Comfy CLI, select Python and click Install ComfyUI. Complete the terminal prompts. EXPECTED The existing Python 3 interpreter is usable, a separate environment is created, and the completed installation can be selected. Existing installations are not overwritten. Model/driver setup remains explicit.
R04 | Required | Not run | NFS disabled preserves normal output | STEPS Disable Network output, select a normal local output folder or your previous custom folder, then start ComfyUI and generate. Open output and the phone gallery. EXPECTED Normal output behavior returns on the new run. The intended local/custom folder is used by the desktop and mobile. The NFS warning is hidden; existing local settings have not been erased.
R05 | Required | Not run | Generated and existing launch scripts | STEPS Create a test launch script using your existing environment and flags, then launch it. Also inspect your current existing-script configuration and launch it with NFS enabled if it forwards "$@". EXPECTED Generated scripts use valid Bash. Flag selections match the script, arguments are retained and the selected output path is supplied correctly. An incompatible existing script shows an understandable error rather than silently using the wrong destination.
R06 | Conditional | Not run | Git update method | STEPS Use a disposable ComfyUI checkout for update testing. Select Git, review the update settings and run an update. Repeat with local tracked/untracked changes if practical. EXPECTED The chosen Git method runs as described. Local changes stop the update safely; nothing is discarded. Logs explain what happened. Normal ComfyUI start/stop remains usable afterward.
R07 | Conditional | Not run | Comfy CLI update method | STEPS Use an intended/disposable ComfyUI environment. Choose its environment folder/Python, select Comfy CLI and run Update. Inspect the command and working directory in the log. EXPECTED The correct environment’s comfy update runs against the intended workspace, with clear errors if CLI/environment is unavailable. It does not silently use the Git update method.
R08 | Required | Not run | Workflow/model/settings compatibility | STEPS Load at least two representative saved workflows or API exports. Check GGUF diffusion model, VAE, text encoder, multiple LoRAs and supported sampler/CFG/steps/resolution controls. Compare the original workflow file before and after. EXPECTED Only mapped literal inputs are changed in submitted copies. Unknown nodes/connections and LoRA defaults are preserved. Unsupported mappings give an understandable error; original workflow files are unchanged.
R09 | Required | Not run | Random and fixed seeds; cancel target | STEPS Generate twice with default randomization, then uncheck it and repeat a fixed seed. Queue jobs from two browser identities and cancel one owned pending/running job where supported. EXPECTED Randomization is checked by default. Fixed-seed reuse is deliberate and may complete instantly through ComfyUI caching. Cancelling targets the correct job and never interrupts another client’s generation; unsupported targeted cancellation is explained.
R10 | Required | Not run | Gallery deletion, comparison and poor connection | STEPS From the PC delete a disposable output image, then check/refresh Gallery. Compare two other images, scroll far down, swap A/B and close on iPhone. Repeat after both images load and the connection becomes briefly poor. EXPECTED Deleted images disappear after synchronization/refresh. Selection/Compare controls and Close remain reachable on the phone. Both comparison images are prepared before use and can be manipulated from the existing in-memory cache. Connection failures can be retried without losing the selection.
R11 | Required | Not run | Prompt history, favorites and image details | STEPS Submit a prompt with a negative prompt, favorite it, search/reuse it, refresh and reopen the app. Inspect generated and directly saved metadata-bearing images; reuse generation settings. EXPECTED History deduplicates identical prompts, positive/negative prompts stay paired, favorites persist, and reuse does not auto-submit. Details show only available values and exact seeds. Comparison and generation reuse still work.
R12 | Required | Not run | Optional password and client privacy | STEPS Test mobile with password disabled, then enable it and test a fresh browser login. Use two separate browser profiles/private sessions to inspect each client’s jobs, drafts/history and image details. EXPECTED Password is optional; when enabled, a fresh client must authenticate. Client histories, active-job state and private generation metadata do not mix. A shared output image may still be visible, but another mobile client’s private metadata is restricted. Displayed QR/URL has no password.
R13 | Required | Not run | Phone reconnect after desktop app restart | STEPS Complete a mobile job and leave an unsent draft. Quit and reopen the desktop app, restart ComfyUI if needed, then reopen the mobile page. Inspect recent jobs/images, settings and history. EXPECTED The browser reconnects without duplicate submission and restores its recent jobs, completed images and saved draft/settings as supported by the same output scope. The app never implies a killed in-flight server job continued running after a full Quit.
R14 | Useful | Not run | Desktop layout, appearance and monitoring | STEPS Resize the main window, expand/collapse monitoring and select an available application style. Watch desktop/mobile stats during sampling, then hide/minimize/restore the window. EXPECTED Buttons and labels remain readable; the terminal stays usable. Monitoring does not stall the UI. Missing metrics show --. Style choice persists and unavailable styles fall back cleanly.
R15 | Conditional | Not run | Crash diagnostics and restart recovery | STEPS Use a disposable app-owned server process, with recovery explicitly enabled. Simulate an abnormal exit, inspect/export diagnostics and test recovery/cancel. Also perform an ordinary Stop. EXPECTED Unexpected exits are recorded and recovery honors its configured limits. A manual Stop does not trigger recovery. Export avoids credentials/secrets and normal shutdown still completes.
R16 | Useful | Not run | LAN, VPN and website/PWA presentation | STEPS Open the displayed URL/QR from LAN and VPN on iPhone, rotate the screen, use the larger prompt editor and reopen from the home screen if you use it. EXPECTED The configured reachable address works without localhost assumptions. Touch controls fit the screen and drafts survive expand/collapse. The ordinary website works over HTTP; full service-worker/PWA behavior is only expected in a secure context.

## Issues
ISSUES ¦ Keep the evidence, then retest
Create one issue per problem. Reference the Test ID and exact build, then paste the error or screenshot/log filename. All rows are blank until you find something.
Critical: data loss/security/unusable app. High: core generation, NFS/fallback or recovery fails. Medium: workaround exists. Low: cosmetic. Close only after retesting.
Overview
Issue ID | Test ID(s) | Severity | Status | Problem summary | Reproduction steps | Expected behavior | Actual behavior / exact error | Evidence reference | Fix build / retest / date